## Slide 1: Theme 12 - DEMP & Constituency Plan
Guidance Plan:
This PPT explains the concept, principles, components and guidelines for District and Constituency level election planning for conducting free and fair elections.
In the opening part, while listing the statutory duties of DEO, the elements for DEMP are introduced.
PPT goes on to explain how the district profile w.r.t social and geographical characteristics, past record during elections, identification of sensitive and critical PS and proper Vulnerability Mapping can help in good planning.
PPT lists the major focus areas such as EVM management, communication plan, effective deployment of security forces, expenditure monitoring, complaints management and intensive training of all personnel.
The latter part of the PPT explains how interaction with political parties, media management, using specialised cells for specific areas of monitoring and SVEEP initiatives become effective tools in executing smooth elections.
The PPT ends with the various components of Booth/BLO level planning, PS management and the critical mistakes on poll-day that can spoil the good work.

## Slide 2: ECI Instructions and Election Planner
Election planner has been prepared and circulated by ECI, by its instruction- No 464/INST/2016- EPS dated 6th January 2017.
It provides general operational framework to election managers.
It is only indicative in nature and does not intend to replace, alter or supplant the extant election related statute, rules or existing guidelines, instructions and procedures mandated by the Commission.
A weekly and daily monitoring mechanism is to be put in place to monitor the implementation of each of the activity.
NB 1: given the diversity and specificity of States, Districts and Assembly Constituencies, DEO/RO must customize the planning process to deal with those specific circumstances. These could include specific law and order inputs and other critical aspects
NB 2: ECI has recently launched a Planning Portal which should be fully utilized and the relevant information required to be fed in the Portal must be ensured within the given timelines

## Slide 3: Objective: This session will provide an understanding regarding preparation of a District Election Plan, its form and flow, its utility in effective election management.
CONTENTS:
Definition of DEMP
ECI instructions on DEMP
Preparation of DEMP- Duties of DEO
Components of DEMP
ACEMP – Definition and Preparation
7. Conclusion

## Slide 4: Definition of DEMP: DEMP is the basic exercise which enables the DEO to plan election management from Micro planning to Macro planning.
Understanding DEMP:
Q. Is DEMP a strategic plan or an operation plan?
A: DEMP is an operational plan with a number of sub-plans in it, essentially for conducting an election.

## Slide 5: Levels of election planning
State Plan.
District Plan.
Assembly Constituency Plan
  ERO / AERO Centric.
  RO/ARO Centric
Booth Level plan
  BLO centric.
  PRO Centric

## Slide 6: DEMP - Process of Preparation
SO collects field data
ARO compiles the data
ARO submits preliminary report to RO
RO checks and makes modifications as required
RO submits to DEO
DEO finalizes the plan
DEMP sent to CEO who suggests changes, if any

## Slide 7: Statutory duties of DEO
Electoral Rolls: S 13AA of RPA 1950, prescribes that subject to the superintendence, direction and control of the CEO, the DEO shall coordinate and supervise all work in the district or in the area within his jurisdiction in connection with the preparation and revision of Electoral Rolls.
Conduct of Elections: As per S20A of RPA 1951, the DEO shall coordinate and supervise all work in the district or in the area within his jurisdiction in connection with the conduct of Elections.
Contd…

## Slide 8: Statutory duties of DEO – contd.
Polling stations: As per S 25 RPA 1951, the DEO shall with previous approval of the ECI make provisions for sufficient number of polling stations and also publish the same
Poll personnel: The DEO shall appoint the Presiding and polling officers for each of the polling station to perform the poll duty (S 26 RPA 1951)
Expenditure Monitoring: As per S 78 RPA 1951, every contesting candidate shall within thirty days of the result lodge his election expenditure account with the DEO and the DEO will report to the Commission under R 89 COER, 1961
Contd…

## Slide 9: Statutory duties of DEO – contd.
The DEO is the custodian of all EVMs, election related papers, ballot boxes, etc. as per R 92 COER 1961.
The District Election Officer is overall in-charge of all activities relating to the preparation and revision of electoral rolls, setting up of polling stations, appointment of poll personnel, EVM storage and FLC. Counting center arrangements, Expenditure monitoring, Communication Plan, grievances redressal and also custodian of all election materials.
NB 1: Booth Level Election Management Plan (BEMP) is an independent imperative in planning as it provides a bottom-up approach and chisels out the BLO and PrO-centric perspective.

## Slide 10
DEMP
District Profile
ER Management
Polling Stations
VM & Criticality
Security Plan & Force Deployment
Force Multiplier Plan
EVM Management
Poll Personnel Plan
MCC
Exp Monitoring
Components of District Election Management Plan
Contd…

## Slide 11
DEMP
Transport & Movement Plan
Complaint Redressal
SVEEP
Training & Awareness Plan
Counting Plan
Material Management Plan
IT Plan
Voter Assistance & Facilitation
PWD Factilites
Interface with Political Parties
Components of District Election Management Plan

## Slide 12: Components of District Plan
1 | District Profile
2 | Electoral Roll Management
3 | Polling Stations and Infrastructure
4 | Vulnerability and Criticality
5 | Security plan and Force Deployment
6 | Communication Plan
7 | EVM Management
8 | Poll personnel management and Welfare
9 | Model Code and enforcement
10 | Expenditure Monitoring
Contd…

## Slide 13: Components of District Plan – contd.
11 | Transport and Movement Plan - Personnel and Machinery
12 | Complaint Redressal
13 | SVEEP – Systematic Voter Education and Electoral Participation
14 | Training and Awareness to all stake holders
15 | IT interventions for better election management
16 | Counting Plan
17 | Material Management
18 | Voter Assistance and Facilitation
19 | PWD Facilities
20 | Interface with Political Parties
 | NB: BEMP – Booth Level Election Management Plan to be integrated with DEMP

## Slide 14: DEMP – creation of District profile
Documents/particulars/records required for creating district profile:
District political map for planning.
Key Statistics- Villages, Gram Panchayats, police stations, urban local bodies, census, elector details, death registrations, roads, connectivity, Administrative set up, Terrain, polling stations, Infrastructure and manpower availability.
General Law and Order.
Past Election snippets- voter turnout.
Past electoral offences.
Sensitivity etc.

## Slide 15: DEMP – Electoral Details
ER statistics analysis – identifying gaps – inaccessible hamlets - strategy for improvement:
District wise, Constituency wise, booth wise electoral statistics.
Analysis of the Health of rolls, identifying gaps and making strategies for improvement.
Roll revision and supervisory mechanism – BLOs/ Designated Officers / multi level checking / Audit of roll revision processes.
Vulnerable and inaccessible hamlets and enrollment challenges.
Monitoring disposal of online applications.
Printing of rolls and its publication.

## Slide 16: DEMP - Major Requisite Information
Polling Stations
Constituency wise no. of polling stations and communication plan
Polling stations categorized by no. of voters
Human Resources and Logistic Plan
Assess manpower requirement at various levels
No. of eligible personnel and no. of personnel required.
Movement Plan
Polling Stations accessible by vehicles
Polling Stations without telephone lines.
Compilation of particulars of officials/officers working at govt. offices/ PSUs
Movement plan for polling parties with route charts, sector wise
Sketch Map of Constituency showing sector routes
Assessment of vehicle requirements
Publication of PS list after approval of ECI
Polling stations , buildings, infrastructure and AMF facilities.
Appointment of poll personnel for the poll
Contd..

## Slide 17: DEMP - Major Requisite Information – contd.
Polling Station-1
Polling Station-3
Polling Station-2
Polling Station-5
Polling Station-6
Polling Station-4
Various Routes to reach Polling stations
Alternate Routes to reach Polling stations
Shortest Routes to reach Polling stations
Road Condition, River, Nala, Bridge
Distance and approximate time to reach
20 km - 30 Min.
40 km - 1 Hr.
10 km - 20 Min.
5 km - 10 Min.
Sketch Map of Constituency showing Sector routes

## Slide 18: DEMP - vulnerability and criticality
Critical and vulnerable PS – identification – force deployment plan – force multipliers:
The DEO with the inputs from the sector officers and the police has to prepare vulnerability mapping of polling stations. The past electoral disturbances, offences, intimidators, persons who may cause vulnerability are all to be taken into account.
Criticality analysis of polling stations have to be made based on the voter turnout and other historical information.
DEO has to make a deployment plan based on the analysis and also plan for force multipliers like video cameras, web cast, micro-observers etc. to cover all hypersensitive locations.

## Slide 19: DEMP - EVM Management
Assessment of Requirement– Polling station, auxiliary booths, reserve –
Request for additional to meet the shortfall.
Obtain EVM-VVPAT consumables- Power packs , paper rolls and batteries from CEO Office.
FLC, Randomisation and storage of machines
Organise EVM-VVPAT awareness programmes at the District, Assembly and booth level for all stake holders.

## Slide 20
Sl No | Description | Start Date | End Date | Status
1 | Training and Capacity Building for all the officers. |  |  | 
2 | Use of Social Media- Disseminate awareness messages though Facebook, Twitter, Instagram at CEO Level |  |  | 
3 | Short films on EVMs-VVPATs to be run on Cable TV. |  |  | 
4 | Distribution of Pamphlets through News papers |  |  | 
5 | Slides of EVM-VVPAT to be played in theatres and cinema halls ahead of elections. |  |  | 
DEMP – EVM & VVPAT Awareness SVEEP Plan
Three Level Planning:
2. District Level Planning:

## Slide 21: DEMP - Human Resources, Poll Personnel Management and Welfare
Requirement of officials – filling up positions
Filling up of AERO/ ERO/ RO and Election branch officials
Filling up all other election related posts at State, District and Assembly level.
Preparation of the data base of poll personnel and collecting and updating their EPIC details.
Estimating the GAP between the required and shortfall make strategies for filling up the GAP.
Implementing Welfare measures.
Provision for Polling Staff Welfare
  Name, Designation and contact details of nodal officer in charge of ensuring polling personnel welfare
  Clear communication of training schedule, dispatching schedule
  Basic amenities at training and dispatching venue
  Facilities at PS to be physically verified and ensured - Adequate facilities for food, refreshments and medical requirements to be made
  Immediate relieving from duty after handover of EVMs and polling materials
  Advance measures to ensure transport facilities for staff
  Special facilities/measures for physically challenged, female polling personnel, death of personnel on duty

## Slide 22: DEMP - District Level Team for Model Code of Conduct
Role and responsibilities of the District MCC monitoring cell:
To constitute Flying Squad, SST and such other enforcement teams required assembly constituency wise for enforcement of MCC by selecting competent officers and staff.
To train officers deployed for Model Code of Conduct teams, political parties and press on Model Code of Conduct.
To provide required men and material to these teams as per ECI guidelines for effective functioning.
To issue time to time instructions to all Model Code of Conduct teams for effective enforcement of Model Code of Conduct.
To circulate latest instructions on Model Code of Conduct among all Model Code of Conduct teams.
To monitor and guide all activities of Model Code of Conduct teams for effective functioning.
To obtain and consolidate Model Code of Conduct reports and forward that same to state Model Code of Conduct Cell.
To attend such other responsibilities entrusted by state Model Code of Conduct Cell.
Sl. No. | Particulars | Designation
1 | District Head | District Election Officer and District Election Officer
2 | Police | Superintendent of Police of the Concerned dist
3 | Income Tax | Income Tax office of the District
4 | Commercial | Commercial Tax Officer of the District
5 | Excise | Deputy Commissioner of Excise of the district.
6 | District MCC Nodal Officer | Nodal Officer

## Slide 23: District Election Expenditure Monitoring Cell
Role and responsibilities of the District election expenditure monitoring cell:
To constitute VST, VVT, AT and Assistant expenditure observer assembly constituency vise by selecting competent officers and staff.
To train officers deployed in the election expenditure monitoring teams, political parties and press on election expenditure monitoring
To provide required men and material to these teams as per ECI guidelines for effective functioning.
To issue time to time instructions to all expenditure monitoring teams for effective implementation of election expenditure monitoring guidelines.
To circulate latest instructions on election expenditure monitoring among all expenditure monitoring teams.
To monitor and guide all activities of election expenditure monitoring teams for effective functioning.
To obtain and consolidate election expenditure monitoring reports and forward that same to state expenditure monitoring cell.
To attend such other responsibilities entrusted by state expenditure monitoring cell.
SL. No. | Official Designation | EEM Designation
1. | District election officer | Chairman
2. | Additional DEO | Member
3. | Nodal officer media monitoring cell | Member
4. | District nodal officer for election expenditure monitoring | Member secretary

## Slide 24: DEMP - Security Plan and Force Deployment
Assessing police personnel requirement – movement plan:
Assessment of Requirement of police personnel (various ranks)
For sector movement and to man polling stations
Prepare return journey for polled EVMs/Polling material, their storage and security plan till counting

## Slide 25: DEMP - Communication Plan
List of landline and cellular connections available near each PS along with particulars of contact person
List of polling personnel/ SO with cellular numbers
Plan mode of communication such as VHF/HF to ensure connectivity in mobile shadow regions

## Slide 26: District Complaint Monitoring Cell
Complaint Monitoring Cell - toll free telephone number – wide publicity - sufficient staff – round the clock shift:
DEOs are instructed to establish Complaint Monitoring Cell with a 24 x 7 Call Centre in the Control Room at the district-level from date of announcement of the elections.
The call centre should be equipped with a toll free telephone number with 3 or 4 hunting lines which will be widely publicized to enable the public to inform the election monitoring machinery regarding corrupt practices, violation of MCC, other electoral offences etc.
A senior competent officer should be in charge of the complaint cell and he will be responsible for receiving and recording the complaints and passing them on to the officer concerned of the Flying Squads which are GPS monitored for prompt action.
The call centre will be provided with sufficient staff to manage the telephone line round the clock in well defined and organized shifts.

## Slide 27: SVEEP as a component in DEMP
Systematic Voters’ Education And Electoral Participation
It handles work related to all aspects of Voters’ Awareness & Education aimed towards improving Electoral Participation and building up a culture of participative democracy among citizens

## Slide 28
Level | Training by | Participants | Duration of training | No. Of Participants
District | District Nodal Officer - EM /SLMT | Expenditure Monitoring Teams | 1 day | 
District | SLMT | Sector Officers | 1 day | 
District | District Nodal Officer- Police /SLMT | Police officers in the rank of Addl. SP/Dy. SP/ Circle Inspector / Inspectors | 1 day | 
District | DEO/RO | Executive Magistrates | 3 hrs | 
District | District Nodal Officer- Income Tax / SLMT | Income Tax Officers | 1 day | 
District | District Nodal Officer- Excise/SLMT | Excise Dept. Officers | 1 day | 
District | SLMT | Political Parties | 3 hrs | 
District | SLMT | Media | 2 hrs | 
Training Plan at District Level

## Slide 29: IT preparations
IT infrastructure for RO/ARO/ERO/AERO – training in IT applications/portal modules – DEO website – Nodal officer as contact point:
DEO should ensure that every AERO/ ERO and the Returning Officer offices are well equipped with enough number of computers, printers, internet facility etc. and data entry operators.
District Information Officer, NIC should be involved in better management.
Organize training to all personnel on ECI IT applications and CEO portal modules.
Prepare DEO web sites for dissemination of election related information.
Appoint a Nodal Officer as a one point contact.

## Slide 30: Counting plan
Identification of Counting Centre/Counting Halls.
Strong Room’s (Storage places for EVM’s)--Pre Poll and Post Poll Strong rooms.
Finalisation of all places of mustering, training Demustering, centres.
IT infrastructure at counting center.
Media room at the Counting center.
Counting staff, training, welfare and deployment.
Sealing , packing post counting materials and machines.
  Identify places for storage of EVMs & Polling materials
  Submit Proposal to CEO for approval from ECI in advance
  Assess Counting Staff availability
  Detail other logistics, media and security arrangements
Key Points:

## Slide 31: Material management
Assessment of material requirement – purchase at CEO level/DEO level – procurement one month in advance:
Assess the hologram requirement well in advance and place request for procurement.
EVM-VVPAT consumables, batteries, power packs, paper seals etc will be procured by CEO Office.
Statutory forms, covers, etc will be supplied by CEO Office.
Appoint a Nodal person to check the requirement and shortfall and to liaison with CEO Office
List the materials to be procured at District Level and complete procurements at least one month in advance
Refer to the relevant chapters of RO Hand Book and ECI instructions dated 23rd Feb 2009, page 6 of Compendium of Instructions, Vol1, Part 2

## Slide 32: Voter assistance and PwD
Helpdesk at all levels – control room 24X7 – mapping of PwD electors and assistance - voter assistance booth on poll-day – home voting for senior citizens and PwD – advance voting:
DEO should ensure that the help desk are functioning at DEO / RO/ ARO/ ERO/ AERO offices.
Control room to record complaints and grievances are functioning 24 X 7.
Identify and map PWD and provide all assistance for their enrollment and voting. Explore online booking of requests.
Prepare DEO web site for voter name search. Keep a copy of alphabetical list at RO Help desk.
Voter assistance booths should be operational on poll day.
NB: New Instructions – DEO and RO to plan for executing Home Voting facility for PwD/80+ and advance voting for essential service category officials

## Slide 33: Interface with Political Parties
Regular meeting to brief them about the Important ECI instructions and schedules.
Briefing them about the provisions of the Model Code and Expenditure monitoring.
EVM- VVPAT Awareness among political Leaders.
Involving all Political Parties in electoral roll revision .
Grievances Redressal meetings.
Meetings for seeking co-operation, feedback and suggestions.

## Slide 34: Role and Responsibilities ERO
Electoral Roll – cleansing of roll - error free – voter awareness/assistance – redressal of grievances:
Electoral Roll, Voter slip, EPIC etc.: The ERO/ AERO are statutorily responsible for preparation and revision of Electoral Rolls.
EROs should seriously take up the activity of cleansing of rolls with the guidance of the CEO and DEO.
Rolls should be all inclusive and error free.
SVEEP, house to house visit, Voter awareness, Voter facilitation, assistance, redressal of roll related grievances etc.

## Slide 35: Role and Responsibilities of RO
Conduct of Elections: Nomination, scrutiny, ballot paper, training, model code, expenditure monitoring, polling stations, poll personnel management, postal ballot management, EVM preparations and demonstrations, welfare of personnel, poll day monitoring and reporting, counting arrangements etc.
ROs are statutorily responsible for conduct of elections in the fee and fair manner in their respective constituencies

## Slide 36: ERO Centric Plan
Plan of action for preparing accurate and error free ER, a prerequisite for the conduct of free and fair elections.
Pre revision activities: Analysis of health of ER, identifying gaps and errors and taking corrective action.
Identifying absent, shifted, dead (ASD) voters and removing them with due procedure.
Rationalization and movement of voters with utmost care and keep all stakeholders and voters well informed at very stage.
Summary revision: Identifying eligible for enrollment- house to house visit by BLOs, Monitoring, supervising BLO work.
Contd…

## Slide 37: ERO Centric Plan – contd.
Timely and prompt action in disposing of all pending applications- online and offline.
Effective grievance redressal mechanism.
Actively Involving political parties, BLAs, RWAs, media in the process of roll revision.
SVEEP activities at booth level, Constituency level. Booth Awareness groups, awareness among students on enrollment, Activating Campus ambassadors.
Wide publicity to roll revision schedules, maximum out reach through all means.
Timely issue of EPIC cards, Voter slips.
Proper account of Holograms and placing timely request for additional supply.

## Slide 38: Assembly segment wise Election Plan (ECI No. 464/INST/2008-EPS dt. 24.10.08)
Compiling details of PS – categorization – Sector formation:
Details of PSs - Total number - categorization of PSs urban/ rural/ polling locations.
Sectors to be formed - one sector (cluster of PSs) should fall on one common road.

## Slide 39: RO centric plan
Plan of action for RO to conduct free, fair and smooth election – training of staff - updating on statutory provisions and latest ECI instructions:
Get to know all Legal and Statutory provisions.
Familiarize with latest ECI instructions on the conduct of elections.
Polling station inspections and ensuring AMF.
Appoint Nodal Officers to assist you in various activities
Training Poll personnel/SO and all other election officials on all legal and procedural aspects of their area of responsibilities.
Nominations, scrutiny, symbol allotment – Update your self with latest ECI instructions and circulars.
Familiarize with the general Law and Order situation, sensitivity of the area, and prepare yourself to tackle unforeseen.

## Slide 40: Sector Management Plan (ECI No. 464/INST/2008-EPS dt. 24.10.08)
Sector formation – synchronizing sector with police mobile team:
Sectors to be formed in advance so that immediately after the announcement of elections, the SOs could be appointed.
Area of the Sector Officers/Zonal Magistrates and police mobile team should be same.

## Slide 41: Premises for various election activities/personnel
Selection of buildings/premises for various activities –
a)For training classes to polling personnel etc.
b)For checking and preparation of EVMs and their storage.
c)For storage of EVMs to be used in training
d)For storage of EVMs AC wise after first randomization.
e)For Dispersal centers
f)For safe custody of polled EVMs and counting of votes.
(Refer ECI Circular No. 51/8/7/2012-EMS dated 19th January, 2012 for a) to e) above)
g)For boarding and lodging of central forces/ outside police forces
h)For boarding and lodging of polling personnel, if required.
Contd…

## Slide 42: Control Room/MCC Teams/IT activities
Control Room - To be well equipped
MCC Teams - complaint monitoring system.
(i) Nodal Officer
(ii) Formation of MCC team AC wise.
(iii) Register to be maintained.
ATR and daily monitoring
IT related activities - a technical team comprising at least one programmer and two data entry operators must be available full time at district level (ECI No. PPS/DEC/ JP/2006 dated 15-12-2006)
Contd…

## Slide 43: Formation of various cells
Contd…
Polling personnel
Facilitation center (Helpline & Control Room)
Polling stations
Media center/cell
Electoral Roll
EVMs
Transportation arrangements
Complaint monitoring
Printing of Postal Ballots and EVM ballots
Election Expenses
Issue of Postal Ballots/ EDC
Procurement and distribution of election materials
Deputing staff and formation of various cells for general arrangements - Duties to be assigned for following events:

## Slide 44: Formation of various cells – contd.
Deputing staff and formation of various cells for general arrangements - Duties to be assigned for following events:
Route Chart preparation - sector movement plan
Liaisoning with Observers
Counting Staff
Issue of Identity Card
Training
Micro Observe
Polling personnel welfare
Computerization/ Randomization
Communication plan,
Arrangements at Distribution Centre, reception Centre
Vulnerability Mapping
Counting center
Critical Polling stations
Law and Order
Model Code of conduct and
videography
Police Personnel
Zonal officer/Sector officers
Statistical Data Cell
Distribution of voter slip

## Slide 45: Meeting with political parties
Meeting with political parties/Standing Committee - Meeting as often as may be convenient after declaration of election
Appeal to cooperate in the observance of model code of conduct for free and fair elections and to maintain law and order
Minutes be drawn - Not to be used as mere formality.

## Slide 46
Activities of Media Cell:
Nodal Officer to coordinate all activities
Holding meetings with media
Giving information on nominations, affidavits, etc and other events - Sharing other information
Coverage on poll day
Coverage on counting day
Authority letters.
Media Cell

## Slide 47: Facilities for Observers [ECI's No. 464/OBS/2007/PLN-I dt. 9-1-2007 and No. 464/INST/ 2007/PLN-I dt. 12.10.2007]
Facilities and logistics support for Observer – personnel to assist:
Boarding, lodging, transport and security to be arranged by DEO.
Stationary, wireless communication, guide and secretarial assistance be provided.
Contingency expenditure, if any, incurred by observer will also be reimbursed
Fax machine of district administration be used by Observer on a priority basis and confidentiality be maintained
One telephone line is sufficient for use of more than one Observer being housed in same premises.
Contd…

## Slide 48
STD telephone with fax facility at counting centers.
Give constituency maps, list of PSs, table of contents of electoral rolls, telephone numbers, book-let containing plan of election and counting of votes.
Proper transport from nearest railway station/airport to constituency.
No Guard of Honor - No escort car/pilot or advance pilot.
Place of stay, phone number and dates of visits of Observer should be publicized.
Food arrangements by district administration
Every Observer will be provided a video camera and a videographer from the day he reaches the constituency.
If suitable Government Guest Houses not available provide alternative accommodation in consultation with CEO.
TA / DA - be drawn from parental ministry / department / office
Facilities for Observers – contd.

## Slide 49: Restrictions on the Printing of pamphlets, posters etc., [ECI's No. 3/9(ES008)94-JS II/5196 dt. 2.9.94, No. 3/9/2004/JS II dt. 24.8.2004 & No. 3/9/2007/JS II dt. 16.10.2007 and S 127A RPA 1951]
Ensure whether printers and publishers are complying with the provisions of S 127A RPA 1951.
All the printing presses shall be informed within 3 days of announcement of election in writing by the District Magistrate to furnish information and printed material as required S 127A RPA 1951 - Attention towards provisions of S 77(1) and 127A of RPA and S 171 H of IPC and ECI's directions may also be drawn.
Contd…

## Slide 50
Four copies of such printed material along with declaration of the publisher shall be furnished to DM/DEO by the printer within 3 days of printing.
List of all the election pamphlets, posters etc shall be exhibited on the notice board of DM/DEO.
Surrogate advertisements in print media for/against a political party/candidate - Expenditure involved in such advertisement has to be added to account of election expenses u/s 77(1), hence required to be maintained - S 171H IPC prohibits expenditure without authority from the candidate.
Strict action on violation of the provisions of S 77(1) and 127A RPA 1951, 171H of IPC and ECI’s directions.
A press note should be issued drawing attention towards provisions of S 77(1) and 127A RPA 1951 and S 171H of IPC.
A report be sent to CEO after completion of election.
Restrictions on the Printing of pamphlets, posters etc., - contd

## Slide 51: Feedback about "Dummy Candidates" - measures to be taken (ECI's No. 464/INST/2008/EPS dt. 7.1.2009)
Measures to prevent misuse of vehicle/agent facilities by ‘Dummy Candidates’ to supplement resources of other candidates:
Actual use of vehicles permitted for campaigning be reviewed - Video recording and collecting evidence - Issuing notice.
Before giving permits of vehicles on poll day dummy factor should be considered.
Appointment of polling agents should be tracked.
Close watch on counting agents.
On misuse of permitted vehicle, action u/s 171H IPC to be taken.
On misuse of vehicle authorized for dummy candidate, notice be given to include the expenditure of the candidate who misused the vehicle for his campaigning.

## Slide 52: Free and fair election - Orders to be issued by DM ( 464/instruCtions/ 2009/EPS dated 01.09.2009)
Various statutory/executive orders to be issued by DM to ensure free, fair and peaceful election:
  Suspension of Arms license on review
  Issue of prohibitory orders under S 144 Cr. PC in certain cases (If required).
  Issue of order under defacement of property (Prevention Act).
  Prohibition of sale of liquor (declaration of dry day).
  Order relating to use of loudspeakers.
  Declaration poll day as local holiday (If required).
  Inviting the attention of Govt. Servants towards relevant provisions of MCC and conduct rules.
  Appointment of Sector Magistrate and polling staff
  Appointment of Special Executive Magistrates under CrPC for proper Conduct of Elections (eg. Sector/ Zonal Magistrates for SST and FST).
Contd…

## Slide 53
  Requisition orders regarding buildings for Polling Stations, Counting Centers, Distribution centers, Reception centers etc..
  Requisition order of vehicles.
  Issuing orders to the Petrol pump owners for keeping reserve stock of POL.
  Sending various statistical information and reports to CEO.
Free and fair election - Orders to be issued by DM – contd. ( 464/instruCtions/ 2009/EPS dated 01.09.2009)

## Slide 54: BOTTOM UP APPROACH- Booth Plan
BLO CENTRIC.
PrO CENTRIC

## Slide 55: BLO Centric plan
BLO’s responsibilities – ER work - poll related work – distribution of EPIC/Voter Information Slip:
An accurate and error free electoral rolls are a prerequisite for the conduct of free and fair elections.
Motivating BLOs in their work. Proper booth level awareness about enrollment activities.
Dissemination of roll revision schedule. Involving BLAs, RWAs, BAGs in improving the quality of rolls.
Effective House to House visit to identify eligible voters for enrollment.
Identifying dead, repeat, shifted voters during house to house visit.
Correction of errors.
Timely distribution of EPIC and voter slips

## Slide 56: PrO Centric Plan - Microplanning for booths
Important booth related activities requiring concerted planning:
Booth profile
EVM-VVPAT Handling
Poll personnel and training.
Polling stations and facilities.
SVEEP and reporting
Enforcement.
Reporting Mechanism.

## Slide 57: Booth profile -- the First Step ….
Profile | Details
Define the Polling station | Building name, location, jurisdiction, complete address, Area Map, Nazri Naksha of the Booth. Number of booths in same location
Basic Statistics about the booth | population- Male, Female, gender ratio, Number of electors, EP, wards, Gram Panchayats, villages, hamlets, SC-ST and vulnerable population details. Details of PWDs in the area. Details of VIPs enrolled / left out
Authorities in the Jurisdiction of the Booth | BLO, BAGS, BLAs, AERO, ERO, Designated officers, RWAs in the area, Volunteers, Birth and Death Registration Authorities and their contact details, including the police station and its details
Contd…
Important aspects to capture for creating comprehensive booth profile for better planning

## Slide 58: Booth profile -- the First Step – contd.
Profile | Details
Characteristics | Terrain, details of inaccessible areas, road connectivity, Vulnerable pockets
Historical Characteristics | Previous turnout, criticality, any poll related violence, group clashes, Communal sensitivity
Law and Order situation in the area | Vulnerable pockets identified, No of intimidators identified, NBWs executed, No of preventive detention cases. Total arms available and deposited during previous elections, Any seizure of illegal arms, liquor and cash during previous elections
AMF Availability | Status of AMF and flagging the repair works needed

## Slide 59
Sl No | Description | Start Date | End Date | Status
1 | Training and Capacity Building of BLOs on EVM-VVPAT. |  |  | 
2 | Use Festivals, public gatherings in villages and set up display stalls disseminating information about EVM-VVPAT. |  |  | 
3 | Film screenings on EVM-VVPAT will be conducted at village panchayats. |  |  | 
4 | EVM/VVPAT Posters will be displayed in Public centres like Polling stations, Panchayat Bhavans, PHCs, Ration shops, Banks, Post Offices etc. |  |  | 
5 | Hoarding , Banners, Posters displayed at main locations. |  |  | 
Booth Level Planning - EVM-VVPAT Awareness SVEEP Plan

## Slide 60: Critical Mistakes On Poll Day in the Polling Station
Listing of some of the often-repeated mistakes during mock poll/actual poll:
During Mock Poll on poll day
Not matching the mock poll result of the CU with VVPAT paper slips
Not removing the mock poll slips from VVPAT
Non-deletion of mock poll from CU
During Poll
Conducting mock poll, in case of replacement of VVPAT only. Mock poll not required to be conducted in case of only VVPAT replacement
In case of non functioning of CU or BU replacing only CU or BU. In such case both BU and CU along with VVPAT shall be replaced.
Non-pressing of CLOSE Button after completion of poll
Damaging any seal of BU/CU/VVPAT

## Slide 61: Poll personnel and Training
Proper mustering / collection plan with checklists at counters, informing all well in advance.
PrO should master the list of election materials
Proper training to PrO on setting up the booth, queue management, special facilities to PwD, women, old age at the booth.
Training PrO on the poll procedures –mock poll, maintaining order within the booth, secrecy of voting, tender / challenge voting, handling complaints on VVPAT slips and handling political agents.

## Slide 62: Polling stations and facilities
Arrangements at PS – AMF - Facilitation for specific categories – reporting of events:
AMF at Polling stations.
Convenient transportation and movement plan for personnel.
Arrangements at the booth.
Facilitation for specific categories - PwD, senior citizens and women.
Safe custody of all materials.
ID card to polling agents.
Contd…

## Slide 63: Polling stations and facilities – contd.
SVEEP at the booth:
  Display contesting candidate list.
  Establishing voter assistance desks with alphabetical list, voter slips, voter guide, EVM-VVPAT brochures.
  Posters on ethical voting and the responsibilities of an elector.
Reporting Mechanism:
  Proper communication plan.
  Immediate reporting on poll disturbances.
  Proper training on writing – PrO diary, vote polled tally, paper seal account, register of voters etc.

## Slide 64: CONCLUSION
DEMP or ACEMP Involves meticulous planning that is necessary in the run up of elections to ensure that all the components are delivered on time to achieve a hassle free conduct of election. It is not a mechanical activity, rather involves deep thought process.